## Agile Project Plan - BLANK
AGILE PROJECT PLAN TEMPLATE
| PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS |  | PROJECT DELIVERABLE
| Computer Hardware Shop Management System | Dr, Ashwyn Kumar | 2022-01-21 | 2022-02-15 |  |  |  | SCOPE STATEMENT | Being a computer system, the system has lots of scope. It not only carried out work faster but also efficiently. A lots of manual work like searching ,personal alias is reduced to a large extent. As this is computerized, system the manager is completely depends on computer for accessing details about students. Here incase there is power failure or some hardware problem which cannot be fixed easily, the manager cannot continue this work. He gets struck in the middle of the day and this dealing need to be postponed. Also the software need to be maintained properly from time to time, that is if it requires being updated or modified etc. then the manager need to take care of it.
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
| Sprint 1 | Computer Hardware Shop Login Page
| Feature 1 | Login Page | Deepak Mane | Design attractive login page take email id and password check both are same redirect to dashbord else display error. | 2022-01-21 | 2022-01-21 | 1 | Complete | No
| Sprint 2 | Dashboard
| Feature 4 | File Menu | Deepak Mane |  | 2022-01-22 | 2022-01-23 | 1 | Complete | No
| Feature 5 | Master Menu | Darshan Bhosale |  | 2022-01-23 | 2022-01-26 | 4 | Complete | No
| Feature 6 | Transaction Menu | Kunal Nevkar |  | 2022-01-26 | 2022-01-30 | 5 | Complete | No
| Sprint 3 | View Reports
| Feature 7 | Search Menu | Shrinivas Kamlapurkar |  | 2022-01-30 | 2022-02-02 | 3 | Complete | No
| Feature 8 | Reports Menu | Kapil Varsale |  | 2022-02-02 | 2022-02-05 | 3 | Complete | No
| Feature 9 | Utilities | Darshan Bhosale |  | 2022-02-05 | 2022-02-05 | 1 | Complete | No