## Agile Sprint Backlog - BLANK
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
Computer Hardware Shop Login Page
Login Page |  | Deepak Mane | Complete | 1 | 1
Dashboard
File Menu |  | Deepak Mane | Complete | 1 | 1
Master Menu |  | Darshan Bhosale | Complete | 4 | 1 | 1 | 1 | 1
Transaction Menu |  | Kunal Nevkar | Complete | 5 | 1 | 1 | 1 | 1 | 1
View Reports
Search Menu |  | Shrinivas Kamlapurkar | Complete | 3 | 1 | 1 | 1
Report Menu |  | Kapil Varsale | Complete | 3 | 1 | 1 | 1
Utilities |  | Darshan Bhosale | Complete | 1 | 1
TOTAL |  |  |  | 18 | 7 | 4 | 4 | 2 | 1 | 0